## Sheet1
Question |  |  | Result
Task Name | Duration (day) | Predecessors | Task Name | Start | Finish
1 | 5 |  | 1 | 2025-04-01 | 2025-04-05
2 | 4 | 1FF | 2 | 2025-04-02 | 2025-04-05
3 | 3 | 2FS+1 day | 3 | 2025-04-07 | 2025-04-09
4 | 2 | 1FS+5 days | 4 | 2025-04-11 | 2025-04-12
5 | 2 | 4FS+3 days | 5 | 2025-04-16 | 2025-04-17
6 | 6 | 2FS+1 day,5FF | 6 | 2025-04-12 | 2025-04-17
7 | 7 | 5 | 7 | 2025-04-18 | 2025-04-24
8 | 2 | 4FF | 8 | 2025-04-11 | 2025-04-12
9 | 3 | 7FF,8FS+1 day | 9 | 2025-04-22 | 2025-04-24
Challenge 230: Project Tasks!
The question table provides the tasks of a project, with task dependencies listed in the predecessors column (details of each dependency are provided in the comments).
Based on this information, and assuming Task 1 starts on 1/4/2025, calculate the start and finish dates for all the tasks.
In this case, the highlighted cells indicate that Task 2 should start at least 5 days after the completion of Task 1.
The "4FF" relation for Task 8 means that both Task 8 and Task 4 must finish on the same day.
Using this information, calculate the start and finish dates for all tasks accordingly.